## Main
Change in
Project Name | City | County | GPS Coordinates | Facility Type | Segment | Territory | Project Stage | Announced Load* | Initial In Service Date | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | New Project? | Announced Load | Load Ramp | Project Stage | Initial Service Date
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 3500 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2187 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service* | 3210 | 2028-06-01 | 0 | 0 | 0 | 1200 | 1300 | 2300 | 2700 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 |  |  | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 3000 | 2027-12-01 | 0 | 0 | 5 | 380 | 760 | 1140 | 1500 | 1880 | 2260 | 2640 | 3000 | 3000 | 3000
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 2000 | 2028-06-01 | 0 | 0 | 0 | 250 | 500 | 750 | 1000 | 1250 | 1500 | 1750 | 2000 | 2000 | 2000
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 2000 | 2028-06-01 | 0 | 0 | 0 | 400 | 800 | 1200 | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 2000 | 2028-06-01 | 0 | 0 | 0 | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1600 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 400 | 900 | 1300 | 1600 | 1600 | 1600 | 1600 | 1600
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1520 | 2028-06-01 | 0 | 0 | 0 | 140 | 280 | 560 | 1040 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 |  | Y | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1500 | 2027-12-01 | 0 | 0 | 10 | 505 | 755 | 1005 | 1255 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 1500 | 2028-06-01 | 0 | 0 | 0 | 20 | 500 | 1000 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 1463 | 2027-12-01 | 0 | 0 | 150 | 400 | 1200 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Contract for Electric Service | 1429 | 2024-04-26 | 400 | 768 | 1146 | 1290 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429 | 1429
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1400 | 2028-06-01 | 0 | 0 | 0 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1400 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 400 | 700 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 1400 | 2027-12-01 | 0 | 0 | 150 | 150 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 1400 | 2028-06-01 | 0 | 0 | 90 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1236 | 2029-06-01 | 0 | 0 | 0 | 0 | 36 | 517 | 998 | 1236 | 1236 | 1236 | 1236 | 1236 | 1236 |  | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 1200 | 2028-06-01 | 0 | 0 | 0 | 300 | 600 | 900 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1200 | 2027-12-01 | 0 | 0 | 90 | 450 | 810 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1200 | 2027-12-01 | 0 | 0 | 100 | 300 | 450 | 650 | 850 | 1050 | 1200 | 1200 | 1200 | 1200 | 1200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1200 | 2027-12-01 | 0 | 0 | 150 | 200 | 400 | 600 | 800 | 1000 | 1200 | 1200 | 1200 | 1200 | 1200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1200 | 2027-12-01 | 0 | 0 | 5 | 80 | 325 | 610 | 910 | 1170 | 1200 | 1200 | 1200 | 1200 | 1200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1200 | 2028-06-01 | 0 | 0 | 0 | 600 | 900 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 1115 | 2028-06-01 | 0 | 0 | 0 | 450 | 450 | 1115 | 1115 | 1115 | 1115 | 1115 | 1115 | 1115 | 1115
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Multiple Sites | Technical Review | 1020 | 2027-12-01 | 0 | 0 | 5.5 | 10.5 | 500 | 500 | 1020 | 1020 | 1020 | 1020 | 1020 | 1020 | 1020
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 1000 | 2028-06-01 | 0 | 0 | 0 | 250 | 650 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 910 | 2027-12-01 | 0 | 0 | 100 | 370 | 550 | 730 | 910 | 910 | 910 | 910 | 910 | 910 | 910
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 910 | 2027-12-01 | 0 | 0 | 25 | 350 | 550 | 750 | 910 | 910 | 910 | 910 | 910 | 910 | 910
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 901 | 2027-10-01 | 0 | 0 | 120 | 342 | 588 | 823 | 901 | 901 | 901 | 901 | 901 | 901 | 901
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 900 | 2029-06-01 | 0 | 0 | 0 | 0 | 200 | 400 | 800 | 800 | 800 | 800 | 900 | 900 | 900 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 880 | 2029-06-01 | 0 | 0 | 0 | 0 | 300 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | 880 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 860 | 2029-06-01 | 0 | 0 | 0 | 0 | 860 | 860 | 860 | 860 | 860 | 860 | 860 | 860 | 860
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 840 | 2029-06-01 | 0 | 0 | 0 | 0 | 200 | 500 | 500 | 840 | 840 | 840 | 840 | 840 | 840 |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 800 | 2027-01-01 | 0 | 0 | 600 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 751 | 2029-06-01 | 0 | 0 | 0 | 0 | 350 | 500 | 751 | 751 | 751 | 751 | 751 | 751 | 751 |  | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 750 | 2027-12-01 | 0 | 0 | 400 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 750 | 2028-06-01 | 0 | 0 | 0 | 25 | 100 | 200 | 300 | 400 | 500 | 600 | 750 | 750 | 750 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 725 | 2027-12-01 | 0 | 0 | 5 | 77 | 245 | 365 | 485 | 605 | 725 | 725 | 725 | 725 | 725
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 725 | 2027-12-01 | 0 | 0 | 5 | 77 | 245 | 365 | 485 | 605 | 725 | 725 | 725 | 725 | 725
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 700 | 2027-12-01 | 0 | 0 | 100 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | 700 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service | 693 | 2028-06-01 | 0 | 0 | 0 | 1 | 50 | 250 | 450 | 650 | 693 | 693 | 693 | 693 | 693
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 651 | 2029-06-01 | 0 | 0 | 0 | 0 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 648 | 2028-06-01 | 0 | 0 | 0 | 150 | 450 | 648 | 648 | 648 | 648 | 648 | 648 | 648 | 648 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 648 | 2027-12-01 | 0 | 0 | 2 | 10 | 216 | 432 | 648 | 648 | 648 | 648 | 648 | 648 | 648
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 612 | 2027-12-01 | 0 | 0 | 2 | 72 | 360 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | 612 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 600 | 2028-06-01 | 0 | 0 | 0 | 200 | 400 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 600 | 2027-12-01 | 0 | 0 | 1 | 60 | 102 | 204 | 300 | 414 | 510 | 558 | 600 | 600 | 600
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 600 | 2027-12-01 | 0 | 0 | 50 | 250 | 450 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 600 | 2027-12-01 | 0 | 0 | 5 | 204.2 | 454.2 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 600
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 576 | 2027-12-01 | 0 | 0 | 2 | 40 | 240 | 336 | 576 | 576 | 576 | 576 | 576 | 576 | 576
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 567 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 2 | 81 | 162 | 243 | 324 | 567 | 567 | 567
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 550 | 2027-12-01 | 0 | 0 | 5 | 100 | 310 | 500 | 550 | 550 | 550 | 550 | 550 | 550 | 550
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 550 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 400 | 550 | 550 | 550 | 550 | 550 | 550 | 550
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 550 | 2027-12-01 | 0 | 0 | 5 | 162.5 | 312.5 | 500 | 550 | 550 | 550 | 550 | 550 | 550 | 550
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 534 | 2028-06-01 | 0 | 0 | 0 | 100 | 200 | 300 | 400 | 534 | 534 | 534 | 534 | 534 | 534 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Contract for Electric Service | 523 | 2026-12-01 | 0 | 53 | 485 | 523 | 523 | 523 | 523 | 523 | 523 | 523 | 523 | 523 | 523 |  |  |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service | 502 | 2028-06-01 | 0 | 0 | 0 | 184 | 253 | 502 | 502 | 502 | 502 | 502 | 502 | 502 | 502
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 500 | 2027-12-01 | 0 | 0 | 200 | 250 | 350 | 450 | 500 | 500 | 500 | 500 | 500 | 500 | 500
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 500 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 100 | 200 | 350 | 400 | 500 | 500 | 500 | 500
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Technical Review | 500 | 2027-12-01 | 0 | 0 | 20 | 20 | 20 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 480 | 2027-12-01 | 0 | 0 | 10 | 10 | 143 | 244 | 345 | 447 | 480 | 480 | 480 | 480 | 480
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 455 | 2027-12-01 | 0 | 0 | 5 | 95 | 365 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 455 | 2029-06-01 | 0 | 0 | 0 | 0 | 5 | 95 | 185 | 275 | 365 | 455 | 455 | 455 | 455
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 455 | 2027-12-01 | 0 | 0 | 5 | 95 | 185 | 275 | 365 | 455 | 455 | 455 | 455 | 455 | 455
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 455 | 2027-12-01 | 0 | 0 | 5 | 95 | 365 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 450 | 2027-12-01 | 0 | 0 | 5 | 5 | 150 | 300 | 450 | 450 | 450 | 450 | 450 | 450 | 450
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 450 | 2027-12-01 | 0 | 0 | 75 | 150 | 225 | 300 | 375 | 450 | 450 | 450 | 450 | 450 | 450
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 432 | 2027-12-01 | 0 | 0 | 1 | 1 | 1 | 67.5 | 144 | 211 | 288 | 355.5 | 432 | 432 | 432
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service | 432 | 2029-06-01 | 0 | 0 | 0 | 0 | 55 | 154 | 229 | 328 | 432 | 432 | 432 | 432 | 432 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 420 | 2028-06-01 | 0 | 0 | 0 | 100 | 300 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 |  |  | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 400 | 2027-12-01 | 0 | 0 | 2.5 | 100 | 150 | 210 | 270 | 330 | 390 | 400 | 400 | 400 | 400 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 365 | 2027-12-01 | 0 | 0 | 5 | 125 | 245 | 365 | 365 | 365 | 365 | 365 | 365 | 365 | 365
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 365 | 2027-12-01 | 0 | 0 | 10 | 124 | 196 | 269 | 341 | 365 | 365 | 365 | 365 | 365 | 365
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 360 | 2027-12-01 | 0 | 0 | 72 | 120 | 168 | 216 | 288 | 360 | 360 | 360 | 360 | 360 | 360
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 360 | 2029-06-01 | 0 | 0 | 0 | 0 | 288 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 350 | 2027-12-01 | 0 | 0 | 1.2 | 86.5 | 155.2 | 224 | 292.7 | 350 | 350 | 350 | 350 | 350 | 350
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 350 | 2028-06-01 | 0 | 0 | 0 | 24 | 64 | 104 | 144 | 184 | 224 | 264 | 350 | 350 | 350
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 325 | 2028-06-01 | 0 | 0 | 0 | 95 | 185 | 325 | 325 | 325 | 325 | 325 | 325 | 325 | 325
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 324 | 2026-06-01 | 0 | 94 | 159 | 213 | 256 | 324 | 324 | 324 | 324 | 324 | 324 | 324 | 324
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 311 | 2026-03-01 | 2 | 6 | 104 | 208 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311 | 311
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 300 | 2028-06-01 | 0 | 0 | 0 | 34 | 74 | 114 | 154 | 194 | 234 | 274 | 300 | 300 | 300
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service | 300 | 2028-06-01 | 0 | 0 | 0 | 100 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 300 | 2027-12-01 | 0 | 0 | 50 | 150 | 250 | 300 | 300 | 300 | 300 | 300 | 300 | 300 | 300
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 288 | 2029-06-01 | 0 | 0 | 0 | 0 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 |  | Y | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 250 | 2029-06-01 | 0 | 0 | 0 | 0 | 10 | 150 | 250 | 250 | 250 | 250 | 250 | 250 | 250 |  | Y | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 250 | 2027-12-01 | 0 | 0 | 25 | 200 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 240 | 2025-01-01 | 21 | 50 | 96 | 155 | 214 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 240 | 2027-12-01 | 0 | 0 | 40 | 80 | 120 | 160 | 200 | 240 | 240 | 240 | 240 | 240 | 240
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Contract for Electric Service | 240 | 2025-11-01 | 15 | 155 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service | 233 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 10 | 107 | 233 | 233 | 233 | 233 | 233 | 233
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service | 225 | 2028-06-01 | 0 | 0 | 0 | 45 | 135 | 225 | 225 | 225 | 225 | 225 | 225 | 225 | 225
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 216 | 2028-01-01 | 0 | 0 | 0 | 72 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 216 | 2025-08-31 | 12 | 90 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 216 | 2029-06-01 | 0 | 0 | 0 | 0 | 144 | 216 | 216 | 216 | 216 | 216 | 216 | 216 | 216
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 216 | 2029-06-01 | 0 | 0 | 0 | 0 | 72 | 144 | 204 | 216 | 216 | 216 | 216 | 216 | 216
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Request for Service | 216 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 72 | 144 | 216 | 216 | 216 | 216 | 216 | 216
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Outside | Contract for Electric Service | 207 | 2025-12-01 | 97 | 131.6 | 148 | 184 | 196 | 207 | 207 | 207 | 207 | 207 | 207 | 207 | 207
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 200 | 2027-12-01 | 0 | 0 | 0.5 | 0.5 | 0.5 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 200 | 2027-12-01 | 0 | 0 | 50 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 200 | 2027-12-01 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 200 | 2027-12-01 | 0 | 0 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Contract for Electric Service | 192 | 2024-01-01 | 22 | 50 | 96 | 155 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192 | 192
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 182 | 2026-06-01 | 0 | 72 | 128 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182 | 182
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Contract for Electric Service | 180 | 2026-03-01 | 0 | 40 | 110 | 175 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 180 | 2029-06-01 | 0 | 0 | 0 | 0 | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 180 | 2026-12-01 | 0 | 15 | 72 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Technical Review | 175 | 2028-06-01 | 0 | 0 | 0 | 40 | 64 | 88 | 112 | 136 | 150 | 175 | 175 | 175 | 175
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 150 | 2024-12-31 | 140 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 145 | 2028-11-01 | 0 | 0 | 0 | 97 | 104 | 145 | 145 | 145 | 145 | 145 | 145 | 145 | 145
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Outside | Technical Review | 144 | 2029-06-01 | 0 | 0 | 0 | 0 | 12 | 84 | 144 | 144 | 144 | 144 | 144 | 144 | 144
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Inside | Contract for Electric Service | 126 | 2025-12-01 | 71 | 87 | 95 | 106 | 115 | 126 | 126 | 126 | 126 | 126 | 126 | 126 | 126
REDACTED | REDACTED | REDACTED | REDACTED | Commercial | Data Center/Crypto | Inside | Contract for Electric Service | 120 | 2026-07-01 | 0 | 0 | 60 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 |  |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Inside | Technical Review | 115 | 2027-12-01 | 0 | 0 | 5 | 5 | 5 | 20 | 65 | 75 | 75 | 75 | 75 | 75 | 115 |  | Y | Y |  | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Request for Service | 105 | 2027-12-01 | 0 | 0 | 5 | 91.4 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Economic Development | Technical Review | 100 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 75 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | Y
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Clean Energy Tech | Inside | Contract for Electric Service | 90 | 2025-12-01 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Outside | Request for Service | 79.479 | 2027-12-01 | 0 | 0 | 26.417 | 46.887 | 46.887 | 64.492 | 64.492 | 79.479 | 79.479 | 79.479 | 79.479 | 79.479 | 79.479
REDACTED | REDACTED | REDACTED | REDACTED | Industrial | Manufacturing | Inside | Technical Review | 50 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 50 |  |  | Y |  | Y
*Since Q2 this project has a Contract for Electric Service currently under Commission review.

## Load Change
Project Name | Q2 2026 | Q1 2026 | Change
REDACTED | 1236 | 480.8 | 755.2
REDACTED | 1520 | 910 | 610
REDACTED | 751 | 500 | 251
REDACTED | 288 | 264 | 24
REDACTED | 250 | 230 | 20
REDACTED | 115 | 240 | -125
Total |  |  | 1535.2

## Ramp Change
| Q2 2026 | [11 empty] | Q1 2026 | [11 empty] | Change
Project Name | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037
REDACTED | 0 | 0 | 0 | 0 | 0 | 2187 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 2187 | 3280.5 | 3500 | 3500 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 219.5 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 1200 | 1300 | 2300 | 2700 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 | 0 | 0 | 1200 | 1500 | 2800 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 | 3210 | 0 | 0 | 0 | -200 | -500 | -510 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 140 | 280 | 560 | 1040 | 1520 | 1520 | 1520 | 1520 | 1520 | 1520 | 0 | 100 | 370 | 550 | 730 | 910 | 910 | 910 | 910 | 910 | 910 | 910 | 0 | -100 | -230 | -270 | -170 | 130 | 610 | 610 | 610 | 610 | 610 | 610
REDACTED | 0 | 150 | 400 | 1200 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 0 | 675 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 1463 | 0 | -525 | -1063 | -263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 0 | 0 | 400 | 700 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 0 | 0 | 0 | 0 | 400 | 700 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 150 | 150 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 0 | 350 | 350 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 0 | -200 | -200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 0 | 36 | 517 | 998 | 1236 | 1236 | 1236 | 1236 | 1236 | 1236 | 0 | 0 | 0 | 480.8 | 480.8 | 480.8 | 480.8 | 480.8 | 480.8 | 480.8 | 480.8 | 480.8 | 0 | 0 | 0 | -444.8 | 36.2 | 517.2 | 755.2 | 755.2 | 755.2 | 755.2 | 755.2 | 755.2
REDACTED | 0 | 0 | 0 | 200 | 500 | 500 | 840 | 840 | 840 | 840 | 840 | 840 | 0 | 0 | 0 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 840 | 0 | 0 | 0 | -640 | -340 | -340 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 0 | 350 | 500 | 751 | 751 | 751 | 751 | 751 | 751 | 751 | 0 | 0 | 0 | 200 | 250 | 350 | 450 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 150 | 250 | 401 | 301 | 251 | 251 | 251 | 251 | 251
REDACTED | 0 | 0 | 0 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 0 | 150 | 400 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 651 | 0 | -150 | -400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 150 | 450 | 648 | 648 | 648 | 648 | 648 | 648 | 648 | 648 | 0 | 1 | 50 | 250 | 450 | 648 | 648 | 648 | 648 | 648 | 648 | 648 | 0 | -1 | 100 | 200 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 0 | 55 | 154 | 229 | 328 | 432 | 432 | 432 | 432 | 432 | 0 | 0 | 55 | 153.7 | 229.3 | 328.3 | 432 | 432 | 432 | 432 | 432 | 432 | 0 | 0 | -55 | -98.7 | -75.3 | -99.3 | -104 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 100 | 300 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 0 | 50 | 250 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 0 | -50 | -150 | -120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 0 | 0 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 288 | 0 | 90 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 264 | 0 | -90 | -264 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24
REDACTED | 0 | 0 | 0 | 10 | 150 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 0 | 10 | 150 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20
REDACTED | 15 | 72 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 15 | 72 | 165 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 60 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 60 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | -60 | -60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
REDACTED | 0 | 5 | 5 | 5 | 20 | 65 | 75 | 75 | 75 | 75 | 75 | 115 | 0 | 0 | 0 | 75 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 240 | 0 | 5 | 5 | -70 | -130 | -85 | -75 | -75 | -75 | -75 | -75 | -125
REDACTED | 0 | 0 | 0 | 0 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 50 | 0 | 0 | 0 | 25 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 38.5 | 50 | 0 | 0 | 0 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stage Change
Project Name | Q2 2026 | Q1 2026
REDACTED | Request for Service | Technical Review

## Removed Projects
Project Name | Announced Load (MW) in Q1 26 | Reason for Removal
REDACTED | 450 | No Decision
REDACTED | 405 | See Note 1
REDACTED | 252 | See Note 1
REDACTED | 180 | See Note 1
REDACTED | 50 | Site
REDACTED | 45 | See Note 1
Total | 1382
Note 1 - Project still active but load now falls below the threshhold to be a large load customer

## Initial Service Change
Project Name | Q2 2026 | Q1 2026 | Change (Months)
REDACTED | Q2 2030 | Q2 2032 | 24
REDACTED | Q4 2027 | Q2 2029 | 18
REDACTED | Q2 2028 | Q4 2027 | -6
REDACTED | Q2 2028 | Q4 2027 | -6
REDACTED | Q4 2026 | Q2 2026 | -6
REDACTED | Q2 2028 | Q4 2027 | -6
REDACTED | Q2 2029 | Q2 2028 | -12
REDACTED | Q2 2030 | Q2 2029 | -12
REDACTED | Q2 2029 | Q4 2027 | -18
REDACTED | Q2 2029 | Q4 2027 | -18

## Projects Added
Project Name | Announced Load* | Created Date
REDACTED | 1500 | 2026-06-11
REDACTED | 900 | 2026-06-30
REDACTED | 880 | 2026-06-17
REDACTED | 750 | 2026-05-01
REDACTED | 700 | 2026-06-02
REDACTED | 612 | 2026-06-30
REDACTED | 534 | 2026-05-07
REDACTED | 400 | 2026-05-11
REDACTED | 200 | 2026-05-06
REDACTED | 200 | 2026-06-30
REDACTED | 100 | 2026-04-21
Total | 6776
*Announced load as of 2037